## Annual Planning
Activities Dates | 2017-02-01 |  |  |  | 2017-03-01 |  |  |  | 2017-04-01 |  |  |  | 2017-05-01 |  |  |  | 2017-06-01 |  |  |  | 2017-07-01 |  |  |  | 2017-08-01 |  |  |  | 2017-09-01 |  |  |  | 2017-10-01 |  |  |  | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01 |  |  |  | 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  | 2019-05-01 | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  | Outputs | Outcome
| Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Mission Goal I - Network, Coalition, and alliance development and maintenance
G & A | 2017-02-01 Week 2: Submit exo-fiscale; budget for N. Amin
Staff development
Member development | 2017-03-01 Week 4: MENA Board elections; 2017-10-01 Week 2: HIC Member Africa region w/s
HLRN Board meeting
HIC General Assembly
G-S consultation
World Social Forum | 2018-03-01 Week 4: WSF (27-31/03) Tunis
World Urban Forum | 2018-02-01 Week 2: World Urban Forum (x-xx/02) Kuala Lumpur
Conference (others) | 2017-04-01 Week 1: L. Zarate, "Dispossession or Right to Remain" @ DRAN, Boston (05/04); 2017-04-01 Week 4: GLTN Arab Learning Exchange, Beirut (24-27/04); 2017-07-01 Week 3: La Via Campesina Intl. Conf. (xx/07) Bilbao; 2017-12-01 Week 1: Arab Land Conference, Dubai (1st half of 11 or 12)
HIC @ 40 publication | 2017-03-01 Week 1: Book production and publication
Mission Goal II - Knowledge creation, empowerment and capacity development; Action research; Dissemination; Methods, Tools, Techniques and Solutions to Ensure H&LR
G & A
Staff development
Land Forum (conf.) | 2017-04-01 Week 2: Presdent concept note to FAO and RLS; 2017-05-01 Week 4: Land Forum preparations; 2017-07-01 Week 3: Land Forum VI event, Tunis; 2017-07-01 Week 4: Land Forum reporting
Land Forum (follow-up) | 2017-06-01 Week 1: Implementation and follow-up of Land Forum outcomes
Land Times
Public info/website/Landpedia
VDB/mapping
Research (general)
Publication (general) | 2017-02-01 Week 1: EvIA Tool / Loss Matrix book
Sanctuary in the city Beirut | 2017-02-01 Week 1: Institutional mapping, Communication strategy Send dcument to Mayor and organise work calendar to draft charter and mobilise participation; 2017-02-01 Week 3: Participant mobilzation, Mapping, Distribute querstionnaires, Literature review, Identify informaiton gaps, Draft assessment and Beirut Charter, Curriculum development; 2017-03-01 Week 4: 3rd w/s, organizational visits; 2017-04-01 Week 1: Distribute questionnaires, Drafting; 2017-04-01 Week 2: Drafting, Consult PDHRE NYC; 2017-04-01 Week 3: Distribute questionnaires, Drafting; 2017-04-01 Week 4: Drafting, W/s reports, Webmounting, Participant mobilization; 2017-05-01 Week 1: Curriculum development, Participant mobilization, Distribute questionnaires; 2017-05-01 Week 2: 4th w/s, organizational visits; 2017-05-01 Week 3: W/s reports, Compile and share final version of outcome documents - all participants; Distribute questionnaires; 2017-05-01 Week 4: Compile comments and elaborate final version; 2017-06-01 Week 1: Analyze survey findings, Finalize assessment, Finalize draft Charter, Produce report; 2017-06-01 Week 2: Launch event; 2017-06-01 Week 3: Finalize assessment & Beirut Charter with event inputs, Final reporting
Methodology dvlpmt. | 2017-02-01 Week 1: Produce methodology and case reports for EvIA publication; 2017-04-01 Week 1: TG curriculum; 2017-05-01 Week 3: TG curriculum; 2017-05-01 Week 4: SPHERE inputs due (30/05); 2017-06-01 Week 1: TG curriculum; 2017-09-01 Week 4: "Rightshop on Land and Conflict" (GLTN) (25–29/09)
Rt2city
Fact-finding mission
OHCHR Pinheiro Principles Handbook | 2017-02-01 Week 2: Handbook development and production; 2017-04-01 Week 1: Core Expert Group Meeting (04/04) Beirut; 2017-07-01 Week 1: Core Expert Group meeting, Beirut (week of 3 or 10/07); 2017-07-01 Week 4: Final version of Pinheiro Principles Handbook
ETO Consortium | 2017-02-01 Week 2: Skype mtg (07/02)
R2FN Watch
RWFAR | 2017-03-01 Week 3: RWFAR workshop (21-22/03) Tunis
USIP: Yemen Land | 2017-02-01 Week 1: Edit drafts case studies; 2017-03-01 Week 1: Consultation mtg; 2017-03-01 Week 2: Finalize report; 2017-04-01 Week 1: Launch event
Training (courses & materials) | 2017-08-01 Week 2: TG training; 2017-09-01 Week 3: TG training; 2017-10-01 Week 3: TG training; 2017-11-01 Week 3: TG training; 2017-12-01 Week 3: TG training
Eviction Impact ♀ w/s | 2017-02-01 Week 2: Project set-up; 2017-04-01 Week 1: Curriculum development; 2017-06-01 Week 3: Training workshop (Guatemala); 2017-06-01 Week 4: Training workshop (Cameroon); 2018-01-01 Week 1: Curriculum development; 2018-03-01 Week 2: Training workshop (Côte d’Ivoire); 2019-01-01 Week 2: Curriculum development; 2019-02-01 Week 2: Training workshop (United States)
Eviction Impact ♀ application | 2017-06-01 Week 3: Local application of EvIA (Guatemala and Cameroon); 2017-09-01 Week 1: Finalize reports: Guatemala (UPR) and Cameroon (CEDaW); 2018-03-01 Week 3: Local application Côte d’Ivoire; 2018-08-01 Week 4: Prepare UPR report: Côte d’Ivoire; 2019-02-01 Week 3: EvIA application (United States)
Eviction Impact ♀ reporting | 2018-07-01 Week 2: Mid-term evaluation; 2018-08-01 Week 3: Submit mid-term evaluation report | [23 empty] | Internal evaluation
ILO Evaluation | 2017-02-01 Week 4: Palestine DWP mission; 2018-06-01 Week 1: Local application of EvIA (Côte d’Ivoire)
Mission Goal III - Advocacy at all levels
G & A | 2018-01-01 Week 1: Strategic Plan review; 2019-01-01 Week 1: Strategic Plan review | [29 empty] | Strategic Plan review | [47 empty] | Strategic Plan review
Staff development
UN political bodies | 2017-02-01 Week 2: Deadline for HRC written submissions (13/02); 2017-02-01 Week 4: HR Council (27/02-24/03); Item 3: SRAH interactive dialogue (01/03) GVA; 2017-03-01 Week 4: Submit reports: Argentina, Benin, Czechia, Gabon, Ghana, Guatemala, Japan, Pakistan, Peru, Rep. Korea, Sri Lanka, Switzerland, Ukraine, Zambia (23/03); 2017-04-01 Week 1: UPR presessional: Algeria, Bahrain, Brazil, Ecuador, Finland, India, Indonesia, Morocco, Netherlands, Philippines, Poland, ZA, UK (4-7/04); 2017-05-01 Week 1: UPR 27th session: Algeria, Bahrain, Brazil, Ecuador, Finland, India, Indonesia, Morocco, Tunisia, UK, Philippines, Poland, Netherlands, ZA (1-12/05); 2017-05-01 Week 2: UPR 27th session: Algeria, Netherlands, Philippines, Poland, ZA (8-10/05); 2017-06-01 Week 2: 35th HRC session (07-23/06); 2017-06-01 Week 3: Submit reports: Bahamas, Barbados, Botswana, Burundi, France, Israel, Liechtenstein, Luxembourg, Mali, Montenegro, Romania, Serbia, Tonga, UAE (22/06); 2017-09-01 Week 2: 36th HRC session (11-29/09) GVA; 2017-09-01 Week 3: Submit reports: Azerbaijan, Bangladesh, Burkina Faso, Cameroon, Canada, Cape Verde, Colombia, Cuba, Djibouti, Germany, Russia, Turkmenistan, Tuvalu, Uzbekistan (21/09); 2017-10-01 Week 1: Presessional: Czechia, Argentina, Gabon, Ghana, Peru, Guatemala, Benin, Rep. Korea, Switzerland, Pakistan, Zambia, Japan, Ukraine, Sri Lanka (xx-xx/10); 2017-11-01 Week 2: 28th session: Czechia, Argentina, Gabon, Ghana, Peru, Guatemala, Benin, Rep. Korea, Switzerland, Pakistan, Zambia, Japan, Ukraine, Sri Lanka (6-17/11); 2017-11-01 Week 3: Submit reports: Azerbaijan, Bangladesh, Burkina Faso, Cameroon, Canada, Cape Verde, Colombia, Cuba, Djibouti, Germany, Russia, Turkmenistan, Tuvalu, Uzbekistan (21/09); 2018-01-01 Week 4: 29th UPR session: France, Tonga, Romania, Mali, Botswana, Bahamas, Burundi, Luxembourg, Barbados, Montenegro, UAE, Israel, Liechtenstein, Serbia (xx/01/xx/02); 2018-02-01 Week 2: Deadline for HRC written submissions (12/02); 2018-02-01 Week 4: HR Council (26/02-xx/03); Item 3: SRAH interactive dialogue (xx/03) GVA; 2018-03-01 Week 3: Submit reports: Belize, CAR, Chad, China, Jordan, Malaysia, Malta, Mauritius, Mexico, Monaco, Nigeria, Rep. Congo, Saudi Arabia, Senegal (22/03); 2018-03-01 Week 4: HR Council (xx/02-xx/03) GVA; 2018-04-01 Week 1: Presessional: Turkmenistan, Burkina Faso, Cape Verde, Colombia, Uzbekistan, Tuvalu, Germany, Djibouti, Canada, Bangladesh, Russia, Azerbaijan, Cameroon, Cuba (xx/04-xx/04); 2018-04-01 Week 4: 30th session: Turkmenistan, Burkina Faso, Cape Verde, Colombia, Uzbekistan, Tuvalu, Germany, Djibouti, Canada, Bangladesh, Russia, Azerbaijan, Cameroon, Cuba (xx/04-xx/05); 2018-06-01 Week 3: Submit reports: Afghanistan, Cambodia, Chile, Comoros, Cyprus, DR, Eritrea, Macedonia, New Zealand, Slovakia, Uruguay, Vanuatu, Viet Nam, Yemen (21/06); 2018-09-01 Week 3: Submit reports: Albania, Bhutan, Brunei, Darussalam, Costa Rica, Côte d’Ivoire, DPR Korea, DRC, Dominica, Equatorial Guinea, Ethiopia, Nicaragua, Norway, Portugal, Qatar (20/09); 2018-10-01 Week 1: Presessional: Saudi Arabia, Senegal, China, Nigeria, Mexico, Mauritius, Jordan, Malaysia, CAR, Monaco, Belize, Chad, Congo, Malta (xx-xx/10); 2018-10-01 Week 4: 31st session: Saudi Arabia, Senegal, China, Nigeria, Mexico, Mauritius, Jordan, Malaysia, CAR, Monaco, Belize, Chad, Congo, Malta (xx/10-xx/11); 2019-01-01 Week 4: 32nd UPR session: New Zealand, Afghanistan, Chile, Viet Nam, Uruguay, Vanuatu, Yemen, Macedonia, Comoros, Slovakia, Eritrea, Cyprus, DR, Cambodia (xx/01-xx/02); 2019-02-01 Week 2: Deadline for HRC written submissions (11/02); 2019-02-01 Week 4: HR Council (xx/02-xx/03); Item 3: SRAH interactive dialogue (xx/03) GVA; 2019-03-01 Week 3: Submit UPR reports: Angola, Bolivia, Bosnia Hzg, Egypt, El Salvador, Fiji, Gambia, Iran, Iraq, Italy, Kazakhstan Madagascar, San Marino, Slovenia (21/03); 2019-03-01 Week 4: HR Council (25/02-xx/03) GVA; 2019-04-01 Week 1: UPR Presessional: Norway, Albania, DRC, Côte d’Ivoire, Portugal, Bhutan, Dominica, DPR Korea, Brunei, Costa Rica, Equatorial Guinea, Ethiopia, Qatar, Nicaragua (xx-xx/04); 2019-04-01 Week 4: 33rd UPR session: Norway, Albania, DRC, Côte d’Ivoire, Portugal, Bhutan, Dominica, DPR Korea, Brunei, Costa Rica, Equatorial Guinea, Ethiopia, Qatar, Nicaragua (xx/04-xx/05) |  |  |  | Submit UPR reports: Armenia, Grenada, Guinea, Guinea-Bissau, Guyana, Kenya, Kiribati, Kuwait, Kyrgyzstan, Laos, Lesotho, Spain, Sweden, Turkey (20/06) | [11 empty] | Submit UPR reports: Andorra, Belarus, Bulgaria, Croatia, Honduras, Jamaica, Liberia, Libya, Malawi, Maldives, Marshall Is, Mongolia, Panama, USA (19/09) |  | UPR Presessional: Italy, El Salvador, Gambia, Bolivia, Fiji, San Marino, Kazakhstan, Angola, Iran, Madagascar, Iraq, Slovenia, Egypt, Bosnia Hzg (xx-xx/10) |  |  | 34th UPR session: Italy, El Salvador, Gambia, Bolivia, Fiji, San Marino, Kazakhstan, Angola, Iran, Madagascar, Iraq, Slovenia, Egypt, Bosnia Hzg (xx/10-xx/11) | [11 empty] | 35th UPR session: Armenia, Grenada, Guinea, Guinea-Bissau, Guyana, Kenya, Kiribati, Kuwait, Kyrgyzstan, Laos, Lesotho, Spain, Sweden, Turkey (xx/02-xx/03) |  | Deadline for HRC written submissions (10/02) |  | HR Council (24/02-xx/03); Item 3: SRAH interactive dialogue (xx/03) GVA |  |  | Submit reports: Australia, Austria, Georgia, Lebanon, Mauritania, Micronesia (Federated States of) Myanmar, Nauru, Nepal, Oman, Rwanda, Saint Kitts, Nevis Sao Tome,Principe St. Lucia (19/03) | HR Council (xx/02-xx/03) GVA | Presessional: Belarus, Liberia, Malawi, Mongolia, Panama, Maldives, Andorra, Bulgaria, Honduras, USA, Marshall Is., Croatia, Jamaica, Libya (xx/04-xx/05) |  |  | 36th session: Belarus, Liberia, Malawi, Mongolia, Panama, Maldives, Andorra, Bulgaria, Honduras, USA, Marshall Is., Croatia, Jamaica, Libya (xx/04-xx/05) | [6 empty] | Submit reports: Belgium, Denmark, Estonia, Latvia, Mozambique, Namibia, Niger, Palau, Paraguay, Seychelles, Sierra Leone, Singapore, Solomon Is., Somalia (18/06) | [11 empty] | Submit reports: Antigua, Barbuda, Greece, Hungary, Ireland, Papua New Guinea, St. Vincent & Grenadines, Samoa, Sudan, Suriname, Swaziland, Tajikistan, Tanzania, Thailand, Trinidad & Tobago (24/09) | Presessional: Micronesia, Lebanon, Mauritania, Nauru, Rwanda, Nepal, Saint Lucia, Oman, Austria, Myanmar, Australia, Georgia, St. Kitts and Nevis, São Tome & Principe (xx-xx/09) |  |  |  | 37th session: Micronesia, Lebanon, Mauritania, Nauru, Rwanda, Nepal, Saint Lucia, Oman, Austria, Myanmar, Australia, Georgia, St. Kitts and Nevis, São Tome & Principe (xx/10-xx/11) | [13 empty] | Deadline for HRC written submissions (08/02) |  | HR Council (22/02-xx/03); Item 3: SRAH interactive dialogue (xx/03) GVA |  |  | Submit reports: Haiti, Iceland, Lithuania, Republic Moldova, South Sudan, Syria, Timor Leste, Togo, Uganda, Venezuela, Zimbabwe (18/03) | HR Council (xx/02-xx/03) GVA
Eviction Impact ♀ reporting: UPR | 2017-03-01 Week 3: Submit UPR report: Guatemala (23/03); 2017-05-01 Week 1: UPR review: India (4/05); 2017-09-01 Week 3: Submit report: Cameroon (21/09); 2017-11-01 Week 2: 28th session: Guatemala; 2018-02-01 Week 1: 29th session: Cameroon; 2018-03-01 Week 3: Submit report: Guatemala; 2018-09-01 Week 3: Submit report to UPR: Côte d’Ivoire (20/09) | 33rd session: Côte d’Ivoire | [14 empty] | Submit report to UPR: USA (19/09)
UN legal bodies | 2017-02-01 Week 4: CESCR presessional: Colombia, Mexico, Rep. Korea, Moldova, Russia (27/02-03/03) GVA; 2017-03-01 Week 4: Sri Lanka Switzerland Ukraine Zambia; 2017-05-01 Week 1: CESCR: parallel report deadline (07/05); 2017-05-01 Week 4: CESCR: Australia, Liechtenstein, Netherlands, Pakistan, Sri Lanka, Uruguay (29/05-23/06) GVA; CEDaW parallel report deadline (09/06); 2017-07-01 Week 1: CEDaW: Barbados, Costa Rica, Italy, Montenegro, Niger, Nigeria, Romania, Thailand (03-21/07) GVA; 2017-08-01 Week 4: CESCR: parallel report deadline (27/08); 2017-09-01 Week 2: CESCR issues deadline (15/09); 2017-09-01 Week 3: CESCR: Colombia, Mexico, Rep. Korea, Moldova, Russia (16/09-06/10) GVA; CEDaW: parallel report deadline (29/09); 2017-10-01 Week 2: CESCR presessional: Argentina, Turkmenistan (09-13/10) GVA; 2017-10-01 Week 3: Burkina Faso, Democratic People's Republic of Korea, Guatemala, Israel, Kenya, Kuwait, Monaco, Nauru, Norway, Oman, Paraguay, Singapore (23/10-17/11) GVA; 2018-01-01 Week 4: CEDaW parallel report deadline (26/01); 2018-02-01 Week 3: CEDaW: Fiji, Luxembourg, Malaysia, Marshall Islands, New Zealand, Republic of Korea, Saudi Arabia, Suriname (12/02-02/03) GVA; 2018-05-01 Week 4: CESCR: Argentina, Turkmenistan, Yemen (28/05-15/06) GVA; CEDaW paralel report deadline (08/06); 2018-07-01 Week 1: CEDaW: Australia, Chile, Indonesia, Mexico, Turkmenistan, Yemen (02-20/07) GVA
UN legal bodies: GC development | 2017-02-01 Week 3: CESCR Day of Discussion: business & HR (02/21); CSO mtg.: GC on Land and ESCRs (22/02) GVA; 2017-08-01 Week 4: Treaty Body Review EGM, Amman (21-22/08)
Eviction Impact ♀ reporting: legal bodies | 2017-06-01 Week 2: Submit report to CEDaW (Guatemala); 2017-09-01 Week 4: CEDaW: submit parallel report: Guatemala (29/09); 2017-10-01 Week 4: Advocacy session @ CEDaW (Guatemala)
UN factual procedures | 2017-02-01 Week 2: WG: HR & business (13-17/03) GVA; 2017-02-01 Week 3: 18th Advisory Council (20-24/02) GVA; 2017-05-01 Week 2: WG: HR of peasants (15-19/05) GVA; 2017-06-01 Week 3: Treaty body chairs (27-30/06) GVA; 2017-06-01 Week 4: 29th Meeting of Chairpersons of Treaty Bodies (27-30/06) NYC; 24th Meeting of special rapporteurs/representatives, independent experts and chairpersons of working groups of the special procedures of the Human Rights Council (27-30/06) GVA; 2017-07-01 Week 2: Experts on indigenous (10-14/07) GVA; 2017-08-01 Week 2: 19th Advisory Council (07-11/08) GVA; 2017-09-01 Week 4: WG: HR & business (25-29/09) GVA; 2017-10-01 Week 3: OEWG: HR & business treaty (23-27/10) GVA; 2017-11-01 Week 3: Forum on HR & business (27-29/11) GVA
UN implementers | 2017-03-01 Week 2: UN-Habitat Gov. Council (8-12/05) Nairobi
UN Implementers: FAO IPC / CSM 4 CFS | 2017-02-01 Week 1: Develop & distribute draft ToR for Follow-up Committee; 2017-03-01 Week 3: IPC mtg: Landless (22/03) Tunis; 2017-04-01 Week 1: OEWG monitoring event (06/04) Rome; 2017-05-01 Week 1: CFS Bureau/Advisory Group (03/05) Rome; 2017-05-01 Week 2: CFS Bureau (08/05) Rome; 2017-10-01 Week 2: CFS 44 & IPC Forum (Rome); 2018-10-01 Week 2: CFS 44 & IPC Forum (Rome) | [18 empty] | CFS 44 & IPC Forum (Rome)
Human Rights Habitat Observatory | 2017-03-01 Week 1: Prospectus for HRHO within UNSDS; 2017-04-01 Week 3: Meet Right to Development Division, OHCHR, New York; 2017-07-01 Week 2: HLPF on SDGs, NYC (10-19/05)
Habitat III | 2017-02-01 Week 4: Implementing NUA in Egypt (02/02); 2017-04-01 Week 1: Implementing NUA in Egypt (02/04)
Regional mechanisms
IFIs | 2017-03-01 Week 3: World Bank Land & Poverty Conf. (20-24/03) WDC
Public advocacy/UAs
Public advocacy/WHD | 2017-09-01 Week 1: Prepare VDB annual report; 2017-10-01 Week 1: Issue VDB report (02/10); 2018-09-01 Week 1: Prepare VDB annual report; 2018-10-01 Week 1: Issue VDB report (01/10) | [13 empty] | Prepare VDB annual report |  |  |  | Issue VDB report (07/10)
Other

## Sheet2
Now the organisation of the calendar is a mix of activites and generic themes - I would suggest to adapt to make project like activities (and activities like projects) - one raw per activity - is the mission goal organisation relevant/important?
Mission Goal I - Network, Coalition, and alliance development and maintenance
G & A
Staff development | Suggest create another category (not necessarely related to mission goals) with activities such as communication strategy, fundraising strategy, call for proposals, staff development,
Member development | What does it mean? Training? Or network mobilisation?
HLRN Board meeting
HIC General Assembly
G-S consultation
World Social Forum | Merging options? Eliminate if it does not have an independent calendar of activities. Include Early 2017 Regional conference on agroecology (FAO). Via Campesina at regional level. Land forum 1st half of 2017. Forum small-farmers. Water and land convergence meeting at Bamako in December?. Solidarity Network for people without state (Badil organiser) between June - September
World Urban Forum
Conference (others)
HIC @ 40 publication
Mission Goal II - Knowledge creation, empowerment and capacity development; Action research; Dissemination; Methods, Tools, Techniques and Solutions to Ensure H&LR
G & A
Staff development
Land Forum (conf.) | Suggest to merge (1st half of 2017)
Land Forum (follow-up)
Land Times
Public info/website/Landpedia
VDB/mapping
Research (general) | Suggest to eliminate no particular/no detailed activities or to rename them with focus theme/project
Publication (general)
Sanctuary in the city Beirut
Methodology dvlpmt.
Rt2city | Suggest to rename Global platform R2C
Fact-finding mission
OHCHR Pinheiro Principles Handbook
ETO Consortium | Suggest to add all network/coalitions HLRN is member of and at least on activity per year with them (ESCR-net, FAO CS mechanism)
R2FN Watch
RWFAR
USIP: Yemen Land
Training (courses & materials)
Eviction Impact ♀ w/s | Why not merged?
Eviction Impact ♀ application
Eviction Impact ♀ reporting
ILO Evaluation
Mission Goal III - Advocacy at all levels
G & A
Staff development
UN political bodies
Eviction Impact ♀ reporting: UPR
UN legal bodies | Declaration of rights of peasants half May - Check> for comments until 1/2 April (first of April to work on comments)
UN legal bodies: GC development | GC on land (end June to have draft supporting land rights - base to be shared with ngos working group); GC on HR and Business activities
Eviction Impact ♀ reporting: legal bodies
UN factual procedures
UN implementers
UN Implementers: FAO IPC / CSM 4 CFS
Human Rights Habitat Observatory
Habitat III
Regional mechanisms
IFIs
Public advocacy/UAs
Public advocacy/WHD
Other
Call for proposals | ETOs, 4 year project proposal of misereor before June
We should add monitoring strategic planning meetings and periodic activities - 1 team meeting per month / general review of strategic planning every 6 months
Lobby activity for Development-Human Rights - FIAN is willing to join a HIC-HLRN initiative to lobby effort, among other things, in the form of a call to all relevant parties in GVA (the HC, treaty body presidents, SRs and Special Procedures, OHCHR bureaus and field presences) and UN-HQ to ensure that the UN Sustainable Development System (a.k.a. SD framework, SD architecture) both refer and defer to state obligations, rather than the UN Human Rights System and its parts strain to become relevant to it. Kate Gilmore (as only she and the Deputy Mayor of Cologne had anything relevant to say on our Quito Special Session panel on refugees/migrants in the urban context). We have decided with some of our friends to engage her in the HRHO objective of making the global policies and composite UN Sustainable Development System more relevant to the treaty bodies and states’ human rights obligations. I hope to rope her into the effort ASAP.
Communication strategy, fundraising strategy, call for proposals, shared drive estructure, network mobilisation